**Harmonized Workplan for the Preparation of CDP**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **ACTIVITIES/ TASKS** | **WEEKS** | | | | | | | | | |
| **January 2018 - September 2019** | | | | **October-December 2019** | | | | **January 2020** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| 1. **MOBILIZATION** | | | | | | | | | | |
| 1. Orientation, organization and tasking |  |  |  |  |  |  |  |  |  |  |
| 1. Preliminary Assessments |  |  |  |  |  |  |  |  |  |  |
| 1. **CHARACTERIZATION AND ANALYSIS** | | | | | | | | | | |
| 1. Module 1: Seminar workshop |  |  |  |  |  |  |  |  |  |  |
| 1. Data collection, review and validation |  |  |  |  |  |  |  |  |  |  |
| 1. Maps and graphics preparation |  |  |  |  |  |  |  |  |  |  |
| 1. Inter- and intra- area analysis |  |  |  |  |  |  |  |  |  |  |
| 1. Population, Settlements and Social Services |  |  |  |  |  |  |  |  |  |  |
| 1. Area Economy |  |  |  |  |  |  |  |  |  |  |
| 1. Infrastructure |  |  |  |  |  |  |  |  |  |  |
| 1. Land Use and Environment |  |  |  |  |  |  |  |  |  |  |
| 1. Institutional Capability |  |  |  |  |  |  |  |  |  |  |
| 1. Module 2: Seminar - Workshop |  |  |  |  |  |  |  |  |  |  |
| 1. Cross-sectoral integration |  |  |  |  |  |  |  |  |  |  |
| 1. Summary of LGU potentials and problems |  |  |  |  |  |  |  |  |  |  |
| 1. Public consultation No. 1 |  |  |  |  |  |  |  |  |  |  |
| 1. **MEDIUM-TERM COMPREHENSIVE DEVELOPMENT PLANNING** | | | | | | | | | | |
| 1. Social Development Plan |  |  |  |  |  |  |  |  |  |  |
| 1. Economic Development Plan |  |  |  |  |  |  |  |  |  |  |
| 1. Environmental Management Plan |  |  |  |  |  |  |  |  |  |  |
| 1. Infrastructure and Physical Development Plan |  |  |  |  |  |  |  |  |  |  |
| 1. Institutional Development Plan |  |  |  |  |  |  |  |  |  |  |
| 1. Local Development Investment Programming and Implementation Instruments |  |  |  |  |  |  |  |  |  |  |
| 1. Public Consultation No. 2: Presentation of the CDP |  |  |  |  |  |  |  |  |  |  |
| 1. **FINALIZATION OF PLANS** | | | | | | | | | | |
| 1. Finalize CDP |  |  |  |  |  |  |  |  |  |  |
| 1. Finalize LDIP |  |  |  |  |  |  |  |  |  |  |
| 1. **PLAN ADOPTION AND APPROVAL** | | | | | | | | | | |
| 1. Submission to LDC for Endorsement to Local Sanggunian |  |  |  |  |  |  |  |  |  |  |
| 1. CDP and LDIP Approval by the Sanggunian |  |  |  |  |  |  |  |  |  |  |